## Overview
IQ-SMART ERP — Scope & Configuration Plan
White-label, single-tenant ERP · config-driven, AI-native · Angular 20 + Node/Express/TypeORM/Postgres/Redis
Project Approach
Config-driven UI | One JSON ViewConfig drives BOTH the List (table) and the Record (form) screen for an entity — no hand-coded screens per entity.
Generic master system | Reference/master data lives in master_registry + master_data (JSONB). CRUD is validated against the entity's form definition. Add a master = seed JSON, no code.
Dynamic form engine | FormDefinition (fields, types, validators, layout) stored in config_resources and served via /api/forms/:slug; rendered by reusable field components.
Document module (transactions) | Documents like PO / Invoice need stateful workflow + activity timeline + comments/queries — delivered by a dedicated document module (planned), reusing the same form + view engine.
Module shell | Context-aware sidebar + Workspace Home launcher; enabled modules & branding come from /api/meta (white-label).
AI-native | Dashboards and records surface AI insights and suggestions (reorder, anomalies, predictions, forecasts), wired progressively per module.
Security | JWT access + refresh-cookie sessions, RBAC (roles & permissions) guarding every module route and master operation.
Priority Legend
P0 | Foundation / Platform — engine + Admin already built (done / in progress).
P1 | Release 1 — Inventory and Procurement (Purchase Orders, Invoices).
P2 | Release 2 — CRM and HR.
P3 | Later — Finance, Sales, Projects, Manufacturing, Assets, Reports.
Scope Summary (auto-counted)
Priority | Scope items | Done | In progress | Planned
P0
P1
P2
P3
Total

## Scope Plan
Priority | Module | Feature / Sub-module | Type | Description | UI Screen(s) | Config-driven | Form Definition (slug) | Data Source / Backend | Workflow (stages) | Panels | AI Capability | Status
P0 | Platform | Authentication & Session | Setup | JWT access token + refresh httpOnly cookie, login, password reset. | Login | N/A | login (public) | auth module /api/auth | — | — | — | Done
P0 | Platform | RBAC — Roles & Permissions | Setup | Role/permission model guarding every route & master op. | List | Partial | — | permission module /api/permissions | — | — | — | In progress
P0 | Platform | Generic Master System | Setup | master_registry + master_data (JSONB); CRUD validated vs form. | List / Record | Yes | per-master | master module /api/masters | — | — | — | Done
P0 | Platform | Dynamic Form Engine | Setup | FormDefinition → reactive form; field components; validators. | Record | Yes | config_resources | form module /api/forms/:slug | — | — | — | Done
P0 | Platform | Config-driven Views (List+Record) | Setup | ViewConfig + ViewResolver → ag-grid list + dynamic record. | List / Record | Yes | via form | view-resolver (FE) | optional | Timeline / Comments | — | Done
P0 | Platform | Module Shell & Workspace Home | Setup | Context-aware sidebar, launcher, module dashboards. | Dashboard | Yes | modules.config | /api/meta | — | — | Insights | Done
P0 | Admin | Masters (registry + CRUD) | Master | Manage all masters; row counts; search. | List / Record | Yes | per-master | /api/masters | — | — | — | Done
P0 | Admin | Form Playground | Setup | Developer reference for the form engine (all field types). | Record | Yes | demo | — | — | — | — | Done
P0 | Admin | Branding / White-label Config | Setup | Product name, logo, enabled modules per deployment. | Setup | N/A | — | config.json + /api/meta | — | — | — | Done
P1 | Inventory | Items | Master | Item catalog — SKU, name, category, UoM, reorder level, status. | List / Record | Yes | master-item | master:item (/api/masters) | — | Timeline / Comments | Reorder hint | Done
P1 | Inventory | Item Categories | Lookup | Classification reference for items. | List | Yes | master-item-category | master (seed) | — | — | — | Planned
P1 | Inventory | Units of Measure (UoM) | Lookup | Measurement units; master-lookup source for Items. | List | Yes | — | master:uom | — | — | — | Done
P1 | Inventory | Warehouses | Master | Storage locations / branches for stock. | List / Record | Yes | master-warehouse | master (new) | — | — | — | Planned
P1 | Inventory | Stock Levels | View / Report | On-hand quantity by item × warehouse, low-stock flags. | List | Partial | — | aggregate API (new) | — | — | Low-stock prediction | Planned
P1 | Inventory | Stock Movements | Transaction | Receipts, issues, adjustments posting to stock. | List / Record | Yes | doc-stock-move | document module (new) | Draft → Posted | Timeline | Anomaly detection | Planned
P1 | Inventory | Transfers | Document | Inter-warehouse stock transfer. | List / Record | Yes | doc-transfer | document module (new) | Draft → Dispatch → Received | Timeline / Comments | — | Planned
P1 | Inventory | Inventory Dashboard | Dashboard | KPIs (items, low stock, value) + AI insights. | Dashboard | Yes | — | aggregate API (new) | — | — | Reorder suggestions | In progress
P1 | Procurement | Vendors | Master | Supplier master — details, terms, contacts. | List / Record | Yes | master-vendor | master (new) | — | Timeline / Comments | Vendor risk | Planned
P1 | Procurement | Vendor Categories | Lookup | Vendor classification reference. | List | Yes | — | master:vendor-category | — | — | — | Done
P1 | Procurement | Purchase Requisitions | Document | Internal request to buy; precedes PO. | List / Record | Yes | doc-requisition | document module (new) | Draft → Submit → Approve | Workflow / Timeline / Comments | Suggest items/vendor | Planned
P1 | Procurement | Purchase Orders (PO) | Document | Order issued to a vendor; core procurement doc. | List / Record | Yes | doc-po | document module (new) | MR → PO → GRN → Invoice → Payment | Workflow / Timeline / Comments | Price & vendor insight | In progress
P1 | Procurement | Goods Receipt (GRN) | Document | Receive goods against a PO; updates stock. | List / Record | Yes | doc-grn | document module (new) | Draft → Posted | Timeline | — | Planned
P1 | Procurement | Purchase Invoices | Document | Vendor bill; 3-way match (PO ↔ GRN ↔ Invoice). | List / Record | Yes | doc-invoice | document module (new) | Draft → Match → Approve → Post → Pay | Workflow / Timeline / Comments | Duplicate & overdue detect | Planned
P1 | Procurement | Procurement Dashboard | Dashboard | Open POs, spend, approvals pending + AI insights. | Dashboard | Yes | — | aggregate API (new) | — | — | Spend insights | Planned
P2 | CRM | Leads | Document | Inbound lead capture and qualification. | List / Record | Yes | doc-lead | document module (new) | New → Qualify → Convert | Timeline / Comments | Lead scoring | Planned
P2 | CRM | Deals / Opportunities | Document | Sales pipeline with stages and value. | List / Record | Yes | doc-deal | document module (new) | Pipeline stages (configurable) | Workflow / Timeline / Comments | Win prediction | Planned
P2 | CRM | Accounts | Master | Customer companies. | List / Record | Yes | master-account | master (new) | — | Timeline | — | Planned
P2 | CRM | Contacts | Master | People linked to accounts/leads. | List / Record | Yes | master-contact | master (new) | — | — | — | Planned
P2 | CRM | Activities | Transaction | Calls, meetings, tasks, notes. | List / Record | Yes | form-activity | module (new) | — | Timeline | Next-best-action | Planned
P2 | CRM | CRM Dashboard | Dashboard | Pipeline KPIs and forecast. | Dashboard | Yes | — | aggregate API (new) | — | — | Forecast | Planned
P2 | HR | Employees | Master | Employee records and profiles. | List / Record | Yes | master-employee | master (new) | — | Timeline / Comments | — | Planned
P2 | HR | Attendance | Transaction | Daily attendance / check-in records. | List / Record | Yes | form-attendance | module (new) | — | — | Anomaly detection | Planned
P2 | HR | Leave Management | Document | Leave application and approval. | List / Record | Yes | doc-leave | document module (new) | Apply → Approve / Reject | Workflow / Timeline | — | Planned
P2 | HR | Payroll | Document | Salary runs and payslips. | List / Record | Yes | doc-payroll | document module (new) | Draft → Process → Pay | Workflow | — | Planned
P2 | HR | Recruitment | Document | Job postings and applicant tracking. | List / Record | Yes | doc-requisition-hr | module (new) | Open → Screen → Interview → Offer | Timeline | Resume screening | Planned
P2 | HR | HR Dashboard | Dashboard | Headcount, leave, attrition KPIs. | Dashboard | Yes | — | aggregate API (new) | — | — | Attrition prediction | Planned
P3 | Finance & Accounting | General Ledger / Payables / Receivables / Reports | Document / Report | Chart of accounts, journals, AP/AR, financial reports. | List / Record / Report | Yes | (per doc) | document + ledger module (new) | Posting workflows | Workflow / Timeline | — | Planned
P3 | Sales | Sales Orders / Quotations / Customers | Document / Master | Order management, pricing, customer master. | List / Record | Yes | (per doc) | document module (new) | Quote → Order → Fulfil → Invoice | Workflow / Timeline / Comments | Pricing insight | Planned
P3 | Projects | Projects / Tasks / Timesheets | Document | Project planning, task tracking, time entry. | List / Record | Yes | (per doc) | module (new) | Plan → Execute → Close | Timeline / Comments | — | Planned
P3 | Manufacturing | Bills of Materials / Work Orders | Master / Document | BOM definitions, production work orders. | List / Record | Yes | (per doc) | document module (new) | Planned → Released → Completed | Workflow / Timeline | — | Planned
P3 | Assets | Assets / Maintenance | Master / Document | Fixed assets, maintenance schedules, depreciation. | List / Record | Yes | (per doc) | master + document (new) | Schedule → Service → Close | Timeline | Predictive maintenance | Planned
P3 | Reports & Analytics | Report Builder / Dashboards | Setup | Cross-module dashboards, KPIs, AI insights. | Dashboard | Partial | — | analytics service (new) | — | — | Cross-module insights | Planned

## Config Building Blocks
Building Block | What it is | Defined in / Source | Reused per | Status
ViewConfig | JSON that drives both the List (columns) and Record (form + panels + workflow) for an entity. | core/config (FE) → backend resource later | entity | Done
FormDefinition | Field list, types, validators, layout (single/two-column); the form to render & validate. | config_resources table · /api/forms/:slug | form | Done
Master Registry | Entity metadata: slug, codeField, labelField, formSlug, managedBy, editable. | master_registry table | master | Done
Master Data | Polymorphic JSONB rows for every master; validated against the form on write. | master_data table · /api/masters/:slug/data | all masters | Done
Field components | type → component map (text, number, select, date, checkbox, master-lookup, …). | dynamic-form/field-registry | shared | Done
Master-lookup | Dropdown whose options come from another master (value=code, label=labelField). | field.optionsSource + /api/masters/:slug/options | shared | Done
Document module | Stateful transactions (PO, Invoice, …): header+lines, state machine, posting. | new backend module | document type | Planned
Workflow / state machine | Ordered stages with current-state stepper; drives allowed transitions. | view config + document state | document | Partial (UI)
Panels | Toggle Activity Timeline / Comments & Queries per entity record. | view config 'panels' | entity | Done (UI)
RBAC permissions | Per-route + per-operation permission checks (e.g. master:create). | permission module + guards | every feature | In progress
AI capabilities | Predictive insights & suggestions per module (reorder, anomalies, forecasts); pluggable per module. | AI service (new) | cross-module | Planned
Branding / Modules | White-label product name/logo + enabled-module flags per deployment. | config.json · /api/meta | deployment | Done